## System_A
SYSTEM REQUIRMENTS (EDC)
COMPONENTS | [6 empty] | RESOURCES (Planning) | [6 empty] | RESOURCES ( Implementation) | [6 empty] | RESOURCES ( Managerial ) | [5 empty] | RESOURCES ( Managerial )
Component | Type | Count | Unit Price + Manuf. Cost | Sub Total | (Person Weeks) | Total Duration (Days) | Role | Count / Task | Type | Total Duration (Days) | Duration of (Days Worked in Cycle HWA:29% -SWA:44%) | AVA. Cost/Day | Sub Total Per System | Role | Count / Task | Type | Duration | Duration of (Days Worked in Cycle HWE: 71% -SWE:56%) | AVA. Cost/Day | Sub Total Per System | Role | Count / Task | Type | Duration | AVA. Cost/Day | Sub Total Per System | Role | Count / Task | Type | Duration | AVA. Cost/Day | Sub Total Per System
Hardware
CPU | 68K0 | 1 | 8 | 8 | 0 | 0 | - | - | - | - | 0 | 0 | 0 | - | - | - | - | 0 | 0 | 0 | Project Manager | 0.5 | In-house | 24 | 275 | 1.65 | Project Analyst | 0.5 | Agency | 16 | 250 | 1
Board | A83-S | 1 | 39 | 39 | 8 | 40 | Hardware Architect | 1 | In-House | 40 | 11.6 | 250 | 1.45 | Hardware Engineer | 3 | In-House/Agency | 13.3333 | 9.4667 | 191.6 | 0.90691
ROM | 8Kb | 1 | 1.5 | 1.5 | 4 | 20 | Hardware Architect | 1 | In-House | 20 | 5.8 | 250 | 0.725 | Hardware Engineer | 3 | In-House/Agency | 6.6667 | 4.7333 | 191.6 | 0.45345
| 32Kb | 1 | 4 | 4 | 4 | 20 | Hardware Architect | 1 | In-House | 20 | 5.8 | 250 | 0.725 | Hardware Engineer | 3 | In-House/Agency | 6.6667 | 4.7333 | 191.6 | 0.45345
RAM | 256KB | 2 | 5 | 10 | 0 | 0 | - | - | - | - | 0 | 0 | 0 | - | - |  | - | 0 | 0 | 0
INTSND | i8042 | 1 | 1.5 | 1.5 | 0 | 0 | - | - | - | - | 0 | 0 | 0 | - | - |  | - | 0 | 0 | 0
GDISP | XVX | 1 | 0 | 0 | 0 | 0 | - | - | - | - | 0 | 0 | 0 | - | - |  | - | 0 | 0 | 0
MISC | Resistors, Caps.. | 100 | 0.5 | 50 | 0 | 0 | - | - | - | - | 0 | 0 | 0 | - | - |  | - | 0 | 0 | 0
I/O | sc100 | 1 | 12 | 12 | 0 | 0 | - | - | - | - | 0 | 0 | 0 | - | - |  | - | 0 | 0 | 0
| sc150 | 1 | 0 | 0 | 0 | 0 | - | - | - | - | 0 | 0 | 0 | - | - |  | - | 0 | 0 | 0
ULA | G1 | 1 | 5 | 5 | 4 | 20 | Hardware Architect | 1 | In-House | 20 | 5.8 | 250 | 0.725 | Hardware Engineer | 3 | In-House/Agency | 6.6667 | 4.7333 | 191.6 | 0.45345
| G2 | 1 | 5 | 5 | 4 | 20 | Hardware Architect | 1 | In-House | 20 | 5.8 | 250 | 0.725 | Hardware Engineer | 3 | In-House/Agency | 6.6667 | 4.7333 | 191.6 | 0.45345
| G3 | 1 | 5 | 5 | 4 | 20 | Hardware Architect | 1 | In-House | 20 | 5.8 | 250 | 0.725 | Hardware Engineer | 3 | In-House/Agency | 6.6667 | 4.7333 | 191.6 | 0.45345
| G4 | 1 | 5 | 5 | 4 | 20 | Hardware Architect | 1 | In-House | 20 | 5.8 | 250 | 0.725 | Hardware Engineer | 3 | In-House/Agency | 6.6667 | 4.7333 | 191.6 | 0.45345
Case | Desktop | 1 | 45 | 45 | 0 | 0 | - | - | - | - | 0 | 0 | 0 | - | - | - | - | 0 | 0 | 0
Storage | 3.5'' Floppy | 2 | 7.5 | 15 | 0 | 0 | - | - | - | - | 0 | 0 | 0 | - | - | - | - | 0 | 0 | 0
Sub Total |  |  |  | 206 | 32 |  |  | 1 |  |  | 46.4 | 11600 | 5.8 | - | 3 |  |  | 37.8667 | 2418.4178 | 3.6276 |  | 0.5 |  | 24 | 6600 | 1.65 |  | 0.5 |  | 16 | 4000 | 1
Software
OS | Synful HB/OS , Kernel, Libs.. | 1 | 0 | 0 | 8 |  | Software Architect | 1 | In-House | 40 | 17.6 | 300 | 2.64 | Software Engineer | 2 | In-House/Agency | 20 | 11.2 | 228.3 | 1.2785 | Project Manager | 0.5 | In-house | 24 | 275 | 1.65 | Project Analyst | 0.5 | Agency | 16 | 250 | 1
| Synful HWCFG | 1 | 0 | 0 | 2 |  | Software Architect | 1 | In-House | 10 | 4.4 | 300 | 0.66 | Software Engineer | 2 | In-House/Agency | 5 | 2.8 | 228.3 | 0.31962
| MCC-McRom, Kennel,Libs,Langs... | 1 | 0 | 0 | 13 |  | Software Architect | 1 | In-House | 65 | 28.6 | 300 | 4.29 | Software Engineer | 2 | In-House/Agency | 32.5 | 18.2 | 228.3 | 2.0775
Softwares | EZ-SYS - EZ Suit | 1 | 0 | 0 | 0 |  | - | - | - | - | 0 | 0 | 0 | - |  |  | 0 | 0 | 0 | 0
Sub Total |  |  |  | 0 | 23 |  |  | 1 |  |  | 50.6 | 15180 | 7.59 |  | 3 |  | 20 | 32.2 | 2450.42 | 3.6756 |  | 0.5 |  | 24 | 6600 | 1.65 |  | 0.5 |  | 16 | 4000 | 1
To
Total Resources | 10
Total Required Days | 247.0667
Total Cost Of Resources in (2000) Systems | 52848.8378
Total Cost Of HW + SW in (2000) Systems | 412000
Total Cost Per System | 231.9933
Total Cost Of 1 Batch (1500) System | 347989.885
Grand Total Of (2000) Systems | 463986.5133
Limitations and Diviations From The Requirement Highlighted In RED

## Dilivery_Plan
BATCH 1 | 1500
Current Budget | 500000
Total Cost | 347989.885
Remaining Budget | 152010.115
Selling Price | 399
Quantity Dilevered | 1000
Quantity Sold | 500
Revenue | 199500
Available Budget | 351510.115
BATCH 2 | 1500
Current Budget | 351510.115
Total Cost | 347989.885
Remaining Budget | 3520.23
Selling Price | 399
Quantity Dilevered | 1000
Quantity Sold | 500
Revenue | 199500
Available Budget | 203020.23